## PMS
Project ID | Project Name | Client Name | Project Type | Project Manager | Priority | Est. Start Date | Expected Project Completion Date | Actual Start Date | Current Stage | Stage Owner | Stage Status | Est Start Date | Est End Date | Actual Start Date 2 | Actual End Date | Stage Delay (Days) | Project Closure Date | Planned Duration (Days) | Days Remaining | Project Status | Time Elapsed % | Remarks
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical | 2026-09-04 |  | 2026-09-04 | LOI Recieved | Bhushan | In Progress | 2026-09-07 | 2026-09-21 |  |  | 0 |  |  |  | In Progress |  | 07.09 -- We still are doing documentation process and then we will recieve LOI, we have demanded to increase the deadline for documentation
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | WO Received | Bhushan
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Site Survey
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Procurement
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Factory Acceptance Test (FAT)
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Manufacturing (if applicable)
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Material Dispatch
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Site Installation
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Testing & Commissioning
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Billing
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Warranty / AMC
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Payment Rcvd
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Project Closed
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Project On Hold
PRJ-0001 |  | DVC | SCADA and Flowmeter |  | Critical |  |  |  | Project Cancelled
Formulas:
Stage Delay (Days) = IF([Est End Date]="","",IF([Actual End Date]<>"",MAX(0,[Actual End Date]-[Est End Date]),MAX(0,TODAY()-[Est End Date])))
Days Remaining = IF([Expected Project Completion Date]="","",MAX(0,[Expected Project Completion Date]-TODAY()))
Time Elapsed % = IF(OR([Est. Start Date]="",[Expected Project Completion Date]=""),"",MIN(100%,MAX(0,(TODAY()-[Est. Start Date])/([Expected Project Completion Date]-[Est. Start Date]))))

## Master Sheet
Project Type | Product / Services | Current Stage | Stage Status | Priority | Stage Owner
DAM Automation | VFD Panel | LOI Received | Not Started | Critical | Bhushan
Canal Automation | PLC Panel | Acceptance Letter | In Progress | High | Site Eng
SCADA Automation | Encoders | EMD Adjustment/Refund | On Hold | Medium | Avishkar
AMC | Ultrasonic Level Transmitter | WO Received | Delayed | Low | Santosh Poddar
JJM – Jal Jeevan Mission | Radar Level Transmitter | Countersign WO & Return | Completed |  | Santosh Poddar
AMR Water Meter | CCTV | Performance Bank Guarantee (PBG) Submission | Cancelled |  | Santosh Poddar
SCADA Automation & AMR Water Meter | Generator | Advance Payment Bank Guarantee (if applicable) |  |  | Site Eng
SCADA and Flowmeter | LED Display Screen | Advance Payment Received (if applicable) |  |  | Site Eng
| Server Rack & Server | Site Survey |  |  | Site Eng
| Software / SCADA | Site Survey Report |  |  | Site Eng
| Solar System | Site Specific BOQ Changes / Variation Approval |  |  | Sanjay
| Batteries & UPS | Billing of Site Survey |  |  | Site Eng
| VFD Panel | JE/AE Sign on Bills |  |  | BO
| PLC Panel | EE Sign on Bills |  |  | BO
| Encoders | Accounts Department |  |  | Governement Official
| Ultrasonic Level Transmitter | Payment of Survey Bill
| Radar Level Transmitter | Procurement
| CCTV | EE Approval
| Generator | Manufacturing (if applicable)
| LED Display Screen | Stage Inspection during Manufacturing (if applicable)
| Server Rack & Server | Factory Acceptance Test (FAT)
| Software / SCADA | FAT Certificate Received
| Solar System | Material Inspection (if applicable)
| Batteries & UPS | Dispatch Clearance
| VFD Panel | Transit Insurance
| PLC Panel with HMI & I/O Cards | Material Dispatch
| Encoders | Material Receipt Certificate at Site
| Ultrasonic Level Transmitter | Site Installation
| Radar Level Transmitter | Recording of MB
| CCTV | Site Installation Approval
| LED Display Screen | Testing & Commissioning
| Server Rack & Server | Final Measurement Entry for RA Bill
| Software / SCADA | Issuance of Testing & Commissioning Certificate
| Solar System | JE/AE Verification
| Batteries & UPS | Billing
| Electromagnetic Flowmeters – Different Sizes | Pre-Audit
| PLC Panel | EE/Accounts Sanction
| PLC | Payment Received
| HMI | Post-Audit
| I/O Cards | Warranty / AMC
| 1 kVA UPS | DLP Tracking / Complaint Register Sign-off
| Pressure Transmitter | Completion Certificate
| Level Transmitter | Release of Performance Guarantee and Security Deposit
| Software / SCADA | Project Closed
| Server | Project On Hold
| Valves | Project Cancelled
| Actuators | Extension of Time (EOT) Granted
| LED Display Screen | Liquidated Damages (LD) Deduction/Waiver
| Water Quality Analysers | Survey MB recording
PLC Panel
PLC
HMI
I/O Cards
1 kVA UPS
Pressure Transmitter
Level Transmitter
Software / SCADA
Server
Valves
Actuators
LED Display Screen
Water Quality Analysers
Electromagnetic Flowmeters – Different Sizes
Pressure Transmitters
Water Quality Analysers
Solar System
Electromagnetic Flowmeters – Different Sizes
Pressure Transmitters
Water Quality Analysers
Solar System
AMR Water Meters – Different Sizes